## Sheet1
Project Name | Task ID | Sub-Task Description | Start Date | End Date | Context | Problem | Solution | Doc Reference | Output Produced | Business Impact | Status: Completed / 🔄 In Progress / ⚠️ Blocked / Planned
Yelp-AI-Data-Platform-End-to-End-Analytics-NLP-CV-PoC | Self Generated Task | Make a new Github repo and connect it to databricks and your device locally. | 13-9-2026 | 13-9-2026 | After Eng Mohamed Abdelaziz request to stop working on Q-Chem Project. I suggested some dataset for him so that he can start giving tasks for the Data & AI Teams. | Eng Mohamed Abdelaziz is still working on creating business cases (use cases) on the yelp dataset and it is taking alot of time. And I have entered the company to prove myself not to sit still. | I started the project on my own then I will adapt based on his tasks. | N/A – repository itself is the deliverable (see Output Produced) | GitHub repository created and successfully connected to both the Databricks workspace and local device for version control. | Version Control so that the company can track my work. | Completed
Yelp-AI-Data-Platform-End-to-End-Analytics-NLP-CV-PoC | Self Generated Task | Test if the repo that you created is working. 1) Check if changes done in Databricks shows in Github 2) Check if changes done on your device locally shows in Github. | 13-9-2026 | 13-9-2026 | After creating the GitHub repository and connecting it to Databricks and the local device in the previous task, needed to confirm the integration was actually working before relying on it for ongoing project work. | Needed to verify that changes made in Databricks sync correctly to GitHub, and that changes made on the local device also sync correctly to GitHub, to avoid losing work or creating version conflicts between environments. | 1) Made a test change in Databricks, pushed it, and confirmed it appeared in the GitHub repo. 2) Made a separate test change locally, pushed it, and confirmed it appeared in the GitHub repo. | N/A | Confirmed two-way sync working correctly between Databricks, local device, and the GitHub repository. | Validates a reliable version-control workflow across environments, reducing risk of lost work and enabling smooth collaboration going forward. | Completed
Yelp-AI-Data-Platform-End-to-End-Analytics-NLP-CV-PoC | Self Generated Task | Start documenting what you are doing in a work report. | 13-9-2026 | 13-9-2026 | Needing a structured way to track daily work after finishing the repo setup/testing tasks | No system existed for logging tasks, reasoning, and outcomes | Created this report with the current column structure and started logging entries | N/A | /00_Docs/00_Work_Report/Ibrahim_Hegazi_Work_Report.xlsx | Visibility for the manager/team and easier status reporting | Completed
Yelp-AI-Data-Platform-End-to-End-Analytics-NLP-CV-PoC | Self Generated Task | Write the code that create the Unity Catalog and the needed Schemas in Databricks. | 13-9-2026 | 13-9-2026 | [6 empty] | Completed
Yelp-AI-Data-Platform-End-to-End-Analytics-NLP-CV-PoC | Self Generated Task | Study and Understand Service Principle so that the work that your account does don't go to waste if the account got deleted. | 14-9-2026 | 14-9-2026
Yelp-AI-Data-Platform-End-to-End-Analytics-NLP-CV-PoC | Self Generated Task | Sit with Eng Ahmed Reda to make an Azure DevOps group for the Data & Analytics Engineers (Interns). | 14-9-2026 | 14-9-2026